## Defects
Sl No | Submitted By | Submitted Date (YYYY-MM-DD) | Description | Severity | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date (YYYY-MM-DD) | Status(Open/Closed) | Remarks
1 | Sudhansu | 2026-01-26 | Low Precision, Recall and F1 scores observed during baseline evaluation of item-based collaborative filtering model on sparse synthetic data. | High | Milestone - 3 | Sudhansu | Standards | Planned fine-tuning by improving interaction generation, creating popularity bias, adjusting weights, increasing interactions per user, and experimenting with recommendation count (k). | 2026-01-28 | Closed | BEFORE: Precision@10: 0.0065, Recall@10: 0.0647, F1@10: 0.0118 AFTER: Precision@20: 0.0204, Recall@20: 0.0603, F1 Score@20: 0.0307, Ideal for a Item CF model trained on synthetic sparse data.
2 | Sudhansu | 2026-02-02 | No fields for products to display in app except product_id making it less user-freindly and interactive | Medium | Milestone-4 | Sudhansu | User Interface | Added fields: product name, description, image to make app look like an e-commerce app | 2026-02-02 | Closed | Added fields on product datasets for the UI.
3 | Sudhansu | 2026-02-04 | After user interaction (like add to cart or buy) in app the page reloads automatically and the state or history of what user have done is erased. | Critical | Milestone-4 | Sudhansu | Logical | Added session state in app to hold changes (history) while the user is logged in. | 2026-02-05 | Closed | The user actions are stored for the session until the user is logged in.
4 | Sudhansu | 2026-02-05 | User live interactions in the app does not have a significant scoring mechanism like in dataset | High | Milestone-4 | Sudhansu | Logical | Added mapping in live app too, now each user action like a click, add to cart or purchase re calculate the recommendations. | 2026-02-05 | Closed | Added a similar logic to calculate scores, giving each type of interaction a specific weight.
5 | Sudhansu | 2026-02-05 | Card layout inconsistencies for larger descriptions, larger product names, such cards appear larger and disproportionate compared to others | Low | Milestone-4 | Sudhansu | User Interface | Set a character limit to display for product names in homepage, so items with longer names does not break the UI. | 2026-02-09 | Closed | Set names > 18 should render... after 18 chars.
6 | Sudhansu | 2026-02-07 | Cold start users are handled, but after logout the cannot log back in with previous login credentials. | Medium | Milestone-4 | Sudhansu | Logical | Added a temp state where only the login crededentials of newly created users are stored and until the app is closed they can log back in with that same credentials. | 2026-02-08 | Closed | Only the username and the login credentials are stored after logout, not the history.
7 | Sudhansu | 2026-02-09 | Navigation issues after user action, also some issues in animation | Low | Milestone-4 | Sudhansu | User Interface | Fixed navigation issues, improved the animation along navigation | 2026-02-09 | Closed
8 | Sudhansu | 2026-02-11 | Page does not load from the top | Low | Milestone-4 | Sudhansu | User Interface | Switched from Streamlit SPA to a modular MPA (Multi-Page Application) | 2026-02-11 | Closed | Switching to MPA resolves the issue of page not loading from top as we have created separate pages for each.
9 | Sudhansu | 2026-02-17 | Recommendations are not updating dynamically based on live user interactions within the app. | High | Milestone-4 | Sudhansu | Standards | Reduced the historical interaction weight to 0.1 and applied a 50x multiplier to live app interactions. Implemented a time decay function, ensuring recommendations are heavily influenced by recent live interactions (e.g., a click from 1 minute ago holds more weight than one from 10 minutes ago). | 2026-02-17 | Closed | Re-ran the evaluation script and the scores effectively doubled: Precision@20: 0.0452, Recall@20: 0.1435, F1-Score: 0.0687.
10 | Sudhansu | 2026-02-19 | User history (such as items in the cart and order history) is entirely erased upon logout. | Medium | Milestone-4 | Sudhansu | Logical | Defined global variables in the server memory to temporarily store user history, mapped directly to their user_id. | 2026-02-20 | Closed | User history is now successfully preserved and retrievable as long as the application remains active.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others