## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status | Remarks
Milestone-1 | Milestone-1 | US-01 | Construct synthetic users, products datasets on which the model would be built upon, knowingly introduced inconsistencies in data generation scripts to mimic real world datasets | Must |  | Sudhansu | Completed | Generated datasets using random and pandas with inconsistencies and saved those files in csv.
Milestone-1 | Milestone-1 | US-02 | Need to clean the generated csv files (users, products) to eliminate the ambiguities present in generation scripts | Must | US-01 | Sudhansu | Completed | Clean the generation scripts and stored the consistent datasets as csv files
Milestone-1 | Milestone-1 | US-03 | Construct interactions from cleaned users, product datasets, to create relationships between products and users, also introducing ambiguities in the interaction_type to be handled during data cleaning | Must | US-02 | Sudhansu | Completed | Generated interactions with fields user_id, product_id and interaction_type which says how the user interacted with the products, keeping fields necessary for model training
Milestone-1 | Milestone-1 | US-04 | Clean the interactions csv file handling the ambiguities in the interaction_type field and using a map to replace the interactions with values (1,3,50,etc.) | Must | US-03 | Sudhansu | Completed | Replaced interactions as values as model understand numbers not strings
Milestone-1 | Milestone-1 | US-05 | Construct a sparse Item-User Matrix with user_id as columns and product_id as index. Impute missing interactions with 0 to prepare for matrix operations. | Must | US-04 | Sudhansu | Completed
Milestone-2 | Milestone-2 | US-06 | As a developer, I want to construct an Item-Based KNN Model that consumes the pre-built User-Item Matrix to generate Top-N product recommendations for a specific User ID. | Must | US-05 | Sudhansu | Completed | Used item based NearestNeigbours metric = "cosine", algorithm = "brute" from sklearn to find the nearest neigbours of specific products and aggreagating the scores and give top-n recommendations of products for a user-id
Milestone-3 | Milestone-3 | US-07 | Generate a script to calculate evaluation scores (Precision, Recall, F1) at K=10 to determine the baseline quality of our Top-10 recommendations. | Must | US-06 | Sudhansu | Completed | Baseline metrics recorded Test interactions: 634 Precision@10: 0.0065 Recall@10: 0.0647 F1@10: 0.0118 Baseline performance on sparse synthetic data
Milestone-3 | Milestone-3 | US-08 | To improve the low baseline scores: Updated the generate interactions logic and used other fields from item/user files to influence product mapping. Increased the interactions count significantly to have more meaningful data patterns and re-ran the pipeline to evaluate Top-10 recommendations. | Should | US-03 | Sudhansu | Completed | Total test interactions evaluated: 22596 Precision@10: 0.4372 Recall@10: 0.5940 F1@10: 0.5187
Milestone-1 | Milestone-3 | US-09 | Found popular products appearing in every recommendation, so introduced a TF-IDF transformer to neutralize popularity bias. Switched evaluation to K=20 (Top-20) to capture a broader range of diverse products and promote rare interactions, then re-ran the pipeline. | Should | US-05 | Sudhansu | Completed | Precision@20: 0.0204, Recall@20: 0.0603, F1 Score@20: 0.0307
Milestone-2 | Milestone-4 | US-10 | Introduced logic for cold start users and refined the "seen" logic: previously, any interaction hid a product. Now, using a score threshold (score < 30), viewed/wishlisted items are kept in the recommendations to support retargeting. Verified this new logic by evaluating the Top-20 recommendations. | Should | US-06 | Sudhansu | Completed | Re-ran the pipeline to view the model scores and found that the scores increased a bit, Users Evaluated: 667, Precision@20: 0.0216, Recall@20: 0.0610, F1 Score@20: 0.0319
Milestone-1 | Milestone-4 | US-11 | Added fields: username, email, password in the user dataset and fields: product name,description, rating, cost, image url for the UI of the app | Should | US-01 | Sudhansu | Completed | Newly added fields are just added for UI purpose and does not influence interactions or so.
Milestone-1 | Milestone-4 | US-12 | Added a script to download images from the image url of the new product datasets and store in local storage and update the image url fields in the product dataset with the local storage link. | Should | US-11 | Sudhansu | Completed | Needed for the user experience as image loading should be instant, the user should be able to see all the product images without any delay
Milestone-1 | Milestone-4 | US-13 | Updated the interactions cleaning script by adding the group by and agg logic to find scores at the bottom removing it from item matrix. | Could | US-08 | Sudhansu | Completed | Now could use the matrix for the transformed scores and interactions for absolute scores.
Milestone-4 | Milestone-4 | US-14 | Generate a script to make pickle files that would be used by the app to give recommendations, avoided using pre-trained matrix for speed and efficiency issues. Generated pickle files containing the model, and reference files (matrix) | Should | US-05 | Sudhansu | Completed | Pickle files are binary files where data is stored in streams of 0s and 1s. It can be accessed and read quicker compared to .csv files and will help in a faster more responsive app.
Milestone-4 | Milestone-4 | US-15 | Initialized the Streamlit web application structure, configuring the page layout to "wide" mode and setting up the sidebar navigation. Created the core routing logic to switch between "Home," "Orders," and "Cart" views using st.radio and conditional rendering. | Must |  | Sudhansu | Completed | Established the base framework.
Milestone-4 | Milestone-4 | US-16 | Implemented a robust data loading pipeline using @st.cache_resource to load the product catalog (CSV), user data, interactions and two binary pickle files: the KNN Model and the Item-User Matrix. This ensures instant access to user history without parsing slow CSVs on every reload. | Must | US-14, US-15 | Sudhansu | Completed | Critical for speed and the new hybrid logic.
Milestone-4 | Milestone-4 | US-17 | Implemented comprehensive session state management using st.session_state to track real-time user data (Cart, Orders, Interaction History, Blacklist). This allows the app to "remember" user actions across different pages without losing context. | Must | US-16 | Sudhansu | Completed | Enables dynamic app behavior.
Milestone-4 | Milestone-4 | US-18 | Developed modular UI components (render_product_card) to display products in a responsive grid layout. Integrated image handling logic to fetch local images or fallback to placeholders, and applied custom CSS for consistent button styling and spacing. | Should | US-16, US-11 | Sudhansu | Completed | Visual layer of the app.
Milestone-4 | Milestone-4 | US-19 | Connected the backend KNN model to the frontend. Implemented "Hybrid Logic" that uses the interactions pickle file to check scores in real-time. Items with score >= 30 (Purchased) are hidden, while items with score < 30 (Wishlisted/Viewed) are prioritized for retargeting. | Must | US-18 | Sudhansu | Completed | The core AI feature (Retargeting enabled).
Milestone-4 | Milestone-4 | US-20 | Created an in-memory authentication system allowing for "Guest Sign Up". Users can create temporary accounts that persist during the browser session, enabling immediate testing of the personalized recommendations without requiring permanent database writes. | Must | US-19 | Sudhansu | Completed | Critical for Project Demo.
Milestone-1 | Milestone-4 | US-21 | Improved the interactions generation file by reducing the total count and integrating an inner loop which locks a particular user_id to a specific category only for 4-6 rows. This increases the depth of the interactions. | Must | US-08 | Sudhansu | Completed | This ensures user have sufficient history in categories(depth) by which model will personalise the recommendations better.
Milestone-1 | Milestone-4 | US-22 | Swapped the TF-IDF transformer with the sklearn normalize L2 as the TF-IDF was making the ultra rare items magnets for recommendations. While it is suitable for large datasets but for our synthetic sparse datasets it was making the recommendations worse. | Must | US-09 | Sudhansu | Completed | Sklearn normalize L2 is based on euclidean length, it is a ratio based transformation where the score is divided by the length which makes overly populated products balanced.
Milestone-2 | Milestone-4 | US-23 | Implemented weighing bias, where the weight of historical data of users are downgraded to 0.1 and live interactions got boosted by a 50 multiplier, this results in quicker change in recommendations based on just a single interaction, which is better for demo purpose. Also between live interactions the one done recently have a high priority for recommendations that one done 10 min ago. | Must | US-10 | Sudhansu | Completed | Recommendations are now much more responsive to live interactions.
Milestone-3 | Milestone-4 | US-24 | Reran the evaluate model script again to re-evalute the Precision, Recall and F1 scores after the changes | Should | US-07 | Sudhansu | Completed | The scores doubled from Precision@20: 0.0216, Recall@20: 0.0610, F1 Score@20: 0.0319 to Precision@20 : 0.0452, Recall@20 : 0.1435, F1-Score : 0.0687 after the changes.
Milestone-4 | Milestone-4 | US-25 | Initialized global variables for Cart,Order History, etc. for every user. Now after logout too the purchases, items in cart and other details are stored temporarily until the app is closed/inactive. | Must | US-17 | Sudhansu | Completed | Added the session state and the global variables in the main file which consists of a function load_data() which runs at the start of the app.